## Template
Overall Capital |  |  | N/A | 2025
Overall Expense | WBS code | 0 | 2351818 | 2025 | 0
P3 ID
[Put P3 ID here] | Type of Spend
Total Variance Expense |  |  |  | S1 | S2 | Total
Variance Percentage |  |  | Budget | [66 empty] | Contingency:
Total Actuals To Date |  |  | Actuals |  |  |  | P3 Actuals: | [61 empty] | Total:
Remaining Spend |  |  | Variance |  |  |  | Forecast Spreadsheet Actuals:
EXPENSE | [6 empty] | Month: |  | 2025-01-31 |  |  |  |  | 2/29/2025 |  |  |  |  | 2025-03-31 |  |  |  |  | 2025-04-30 |  |  |  |  | 2025-05-31 |  |  |  |  | 2025-06-30 |  |  |  |  | 2025-07-31 |  |  |  |  | 2025-08-31 |  |  |  |  | 2025-09-30 |  |  |  |  | 2025-10-31 |  |  |  |  | 2025-11-30 |  |  |  |  | 2025-12-31
Contact for PO/ER | PO Number/ ER Number | PO Start Date | PO end date | Vendor Name | G/L Account | Gross PO Value (USD) | Requisition Title | PO Status | Accrual Reversal Dec | Forecast Jan | Accrual Jan | Actual Jan | Variance (Actuals/Accruals | Accrual Reversal Jan | Forecast Feb | Accrual Feb | Actual Feb | Variance (Actuals/Accruals | Accrual Reversal Feb | Forecast March | Accrual March | Actual March | Variance (Actuals/Accruals | Accrual Reversal Mar | Forecast April | Accrual April | Actual April | Variance (Actuals/Accruals | Accrual Reversal Apr | Forecast May | Accrual May | Accrual May | Variance (Actuals/Accruals | Accrual Reversal May | Forecast June | Accrual June | Actual June | Variance (Actuals/Accruals | Accrual Reversal Jun | Forecast July | Accrual July | Actual July | Variance (Actuals/Accruals | Accrual Reversal Jul | Forecast Aug | Accrual Aug | Actual Aug | Variance (Actuals/Accruals | Accrual Reversal Aug | Forecast Sept | Accrual Sept | Actual Sept | Variance (Actuals/Accruals | Accrual Reversal Sep | Forecast Oct | Accrual Oct | Actual Oct | Variance (Actuals/Accruals | Accrual Reversal Oct | Forecast Nov | Accrual Nov | Actual Nov | Variance (Actuals/Accruals | Accrual Reversal Nov | Forecast Dec | Accrual Dec | Actual Dec | Variance (Actuals/Accruals | Total 2023 | CPA Budget <YEAR> | Comments
| 9500879389 | [7 empty] | 0 | 14487.5 | 0 | 13822.5 |  | 0 | 10212.5 | 19385.28 | 17100 |  | -19385.28 | 21375 | 22813.72 | 20425 |  | -22813.72 | 15390 | 19294.5 | 15247.5 |  | -19294.5 | 17100 | 20952.78 | 11162.5 |  | -20952.78 | 21375 | 30922.5 | 16862.5 |  | -30922.5 | 855 | 14060 | 427.5 |  | -14060 | 0 | 13632.5 | 0 |  | -13632.5 | 0 | 13632.5 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 9500882917 | [7 empty] | 0 | 25857 | 0 | 34040 |  | 0 | 30420 | 62210 | 0 |  | -78320 | 60000 | 121710 | 58648 |  | -140172 | 48000 | 128172 | 20960 |  | -130564 | 48000 | 158564 | 102760 |  | -140102 | 57600 | 117094 | 38368 |  | -98592 | 2400 | 60224 | 0 |  | -60224 | 0 | 0 | 2400 |  | 0 | 0 | 57824 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Previous Period Invoices
Contingency | N/A
Contingency | N/A |  |  | N/A
EXPENSE END
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Using forecast spreadsheet (not P3) - actuals to date + curerent periods accruals and any actuals they might have also hit
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Using forecast spreadsheet (not P3) - budget - (actuals to date + curerent periods accruals and any actuals they might have also hit)

## Forecast Source Data
PO # | 2025 Forecast total Fee | Jan 2025 - FTotal | Feb 2025 - FTotal | March 2025 - FTotal | April 2025 - FTotal | May 2025 - FTotal | June 2025 - FTotal | July 2025 - FTotal | Aug 2025 - FTotal | Sep 2025 - FTotal | Oct 2025 - FTotal | Nov 2025 - FTotal | Dec 2025 - FTotal | Pfizer requested PO | IBM PMA | PO Owner | Work Code | Project Name | Project Start Date | Project End Date | Resource Talent Id | Resource Name | Bill Rate | Location | Resource Status | Forecast Month Hours | Forecast Fee $ | Forecast Expenses $ | Forecast Total $ | Actual Month Hours | Acual Fee $ | Actual Expenses $ | Actual Total $ | Monthly Hours Variance | Hours Billed Flag | Forecast Accuracy | Expense% | Comments | Total Forecast Hours 2025 | Jan 2025 - FFHours | Feb 2025 - FHours | March 2025 - FHours | April 2025 - FHours | May 2025 - FHours | June 2025 - FHours | July 2025 - FHours | Aug 2025 - FHours | Sep 2025 - FHours | Oct 2025 - FHours | Nov 2025 - FHours | Dec 2025 - FHours | Jan 2025 - FFee | Feb 2025 - FFee | March 2025 - FFee | April 2025 - FFee | May 2025 - FFee | June 2025 - FFee | July 2025 - FFee | Aug 2025 - FFee | Sep 2025 - FFee | Oct 2025 - FFee | Nov 2025 - FFee | Dec 2025 - FFee | 2025 Total Forecast Expenses | Jan 2025 - FExpenses | Feb 2025 - FExpenses | March 2025 - FExpenses | April 2025 - FExpenses | May 2025 - FExpenses | June 2025 - FExpenses | July 2025 - FExpenses | Aug 2025 - FExpenses | Sep 2025 - FExpenses | Oct 2025 - FExpenses | Nov 2025 - FExpenses | Dec 2025 - FExpenses | Forecast Total 2025
9500879389 | 49780 | 7457.5 | 4275 | 10687.5 | 7695 | 8550 | 10687.5 | 427.5 | 0 | 0 | 0 | 0 | 0 | No | Ashu | Immanual Thomas | W296Z | Pfizer Digital – GLNS Support S1 2025 | 2025-01-01 | 2025-06-30 | 003A51 | Arun Kumaravelu | 47.5 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 |  | 1048 | 157 | 90 | 225 | 162 | 180 | 225 | 9 | 0 | 0 | 0 | 0 | 0 | 7457.5 | 4275 | 10687.5 | 7695 | 8550 | 10687.5 | 427.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49780
9500879389 | 51015 | 7030 | 5937.5 | 10687.5 | 7695 | 8550 | 10687.5 | 427.5 | 0 | 0 | 0 | 0 | 0 | No | Ashu | Immanual Thomas | W296Z | Pfizer Digital – GLNS Support S1 2025 | 2025-01-01 | 2025-06-30 | 0220B5 | Sesha Sai Sruthi Kocherla | 47.5 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 |  | 1074 | 148 | 125 | 225 | 162 | 180 | 225 | 9 | 0 | 0 | 0 | 0 | 0 | 7030 | 5937.5 | 10687.5 | 7695 | 8550 | 10687.5 | 427.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51015
9500882917 | 94320 | 0 | 0 | 26200 | 20960 | 20960 | 25152 | 1048 | 0 | 0 | 0 | 0 | 0 | Yes | Ashu | Immanual Thomas | W296Z | Pfizer Digital – GLNS Support S1 2025 | 2025-01-01 | 2025-06-30 | C-VM9K | Rafael Sampaio | 131 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 |  | 720 | 0 | 0 | 200 | 160 | 160 | 192 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26200 | 20960 | 20960 | 25152 | 1048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94320
9500882917 | 177957 | 25857 | 30420 | 33800 | 27040 | 27040 | 32448 | 1352 | 0 | 0 | 0 | 0 | 0 | Yes | Ashu | Immanual Thomas | W296Z | Pfizer Digital – GLNS Support S1 2025 | 2025-01-01 | 2025-06-30 | C-RY4V | Srinivas Jakkidi | 169 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 0 |  | 1053 | 153 | 180 | 200 | 160 | 160 | 192 | 8 | 0 | 0 | 0 | 0 | 0 | 25857 | 30420 | 33800 | 27040 | 27040 | 32448 | 1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177957
PO Total

## Transactions Source Data
PO Number | Accounting Period | AP Voucher Number | Vendor Name | WBS Element | GL Invoice Date | GL Posting Date | GL Line Description | Description | Month | GL Transaction Amount | Type | Fiscal Year | Planful Date | Function Code | Sub Function Code | Cost Center* | LT Member* | LT Member -1* | CC Description | CC Level 1 | CC Level 2 | Org | CC Level 4 | CC Level 5 | Major Code | Minor Code | Exp Acct Minor Code - Text | Account* | Expense Account Code | Division Code | Market Code | Value Type | Document Type | Legal Entity | Country | Region | Project Code* | Grouping | GL Transaction Number | GL Invoice Number | Ledger Currency | Local Currency | Transaction Currency | GL MAR Corp Amount | GL Local Amount | GL BER Corp Amount
9500879389 | 202502 | 5107267072 | IBM WW ORDERING AND US INVOICING | IT-FBT0397-OG-US-00 | 2025-02-14 | 2025-02-14 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 2 | 13822.5 | Actual | 2025 | 2025-02-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 51072670722 | C25W938901 | USD | US Dollar | USD | 13822.5 | 13822.5 | 13822.5
9500882917 | 202502 | 5107267040 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-02-14 | 2025-02-14 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 2 | 34040 | Actual | 2025 | 2025-02-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51072670402 | C25W291701 | USD | US Dollar | USD | 34040 | 34040 | 34040
9500879389 | 202502 | 2100077443 | Not assigned | IT-FBT0397-OG-US-00 | 2025-02-24 | 2025-02-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 2 | 19385.28 | Accrual | 2025 | 2025-02-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 2100077443174 | AP2-25 2WM | USD | US Dollar | USD | 19385.28 | 19385.28 | 19385.28
9500882917 | 202502 | 2100077443 | Not assigned | IT-FBT0545-OG-US-00 | 2025-02-24 | 2025-02-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 2 | 62210 | Accrual | 2025 | 2025-02-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100077443177 | AP2-25 2WM | USD | US Dollar | USD | 62210 | 62210 | 62210
9500879389 | 202503 | 2100077864 | Not assigned | IT-FBT0790-OG-US-00 | 2025-03-31 | 2025-03-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 3 | 22813.72 | Accrual | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100077864157 | AP3-25 2WM | USD | US Dollar | USD | 22813.72 | 22813.72 | 22813.72
9500882917 | 202504 | 5107369850 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-04-11 | 2025-04-14 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 4 | 58648 | Actual | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51073698502 | C25291703 | USD | US Dollar | USD | 58648 | 58648 | 58648
9500879389 | 202504 | 5107366814 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-04-11 | 2025-04-11 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 4 | 20425 | Actual | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51073668142 | C25938903 | USD | US Dollar | USD | 20425 | 20425 | 20425
9500882917 | 202504 | 2100078176 | Not assigned | IT-FBT0545-OG-US-00 | 2025-03-31 | 2025-04-07 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 4 | -121710 | Reversal | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007817614 | # | USD | US Dollar | USD | -121710 | -121710 | -121710
9500882917 | 202504 | 2100078226 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-01 | 2025-04-07 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 4 | 16110 | Accrual | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 21000782268 | OPEX -T3 ADJ | USD | US Dollar | USD | 16110 | 16110 | 16110
9500882917 | 202504 | 2100078519 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-28 | 2025-04-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 4 | 112062 | Accrual | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007851915 | # | USD | US Dollar | USD | 112062 | 112062 | 112062
9500882917 | 202504 | 2100078580 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-29 | 2025-04-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 4 | -18462 | Reversal | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007858011 | OPEX -T3 ADJ | USD | US Dollar | USD | -18462 | -18462 | -18462
9500879389 | 202504 | 2100078170 | Not assigned | IT-FBT0790-OG-US-00 | 2025-03-31 | 2025-04-07 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 4 | -22813.72 | Reversal | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100078170157 | AP3-25 2WM | USD | US Dollar | USD | -22813.72 | -22813.72 | -22813.72
9500879389 | 202504 | 2100078515 | Not assigned | IT-FBT0790-OG-US-00 | 2025-04-28 | 2025-04-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 4 | 19294.5 | Accrual | 2025 | 2025-04-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100078515140 | AP4-25 2WM | USD | US Dollar | USD | 19294.5 | 19294.5 | 19294.5
9500879389 | 202503 | 5107325007 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-03-17 | 2025-03-17 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 3 | 17100 | Actual | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51073250072 | C25938902 | USD | US Dollar | USD | 17100 | 17100 | 17100
9500879389 | 202503 | 9005719467 | Not assigned | IT-FBT0397-OG-US-00 | 2025-03-27 | 2025-03-15 | RC03-9500879389-FIXING WBS CODE | RC03-9500879389-FIXING WBS CODE | 3 | -15096 | Reclass | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 900571946771 | AP03 2025 WDAC - | USD | US Dollar | USD | -15096 | -15096 | -15096
9500879389 | 202503 | 9005719467 | Not assigned | IT-FBT0397-OG-US-00 | 2025-03-27 | 2025-03-15 | RC03-9500879389-FIXING WBS CODE | RC03-9500879389-FIXING WBS CODE | 3 | -18112 | Reclass | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 900571946778 | AP03 2025 WDAC - | USD | US Dollar | USD | -18112 | -18112 | -18112
9500879389 | 202503 | 9005719467 | Not assigned | IT-FBT0790-OG-US-00 | 2025-03-27 | 2025-03-15 | RC03-9500879389-FIXING WBS CODE | RC03-9500879389-FIXING WBS CODE | 3 | 15096 | Reclass | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 900571946774 | AP03 2025 WDAC - | USD | US Dollar | USD | 15096 | 15096 | 15096
9500879389 | 202503 | 9005719467 | Not assigned | IT-FBT0790-OG-US-00 | 2025-03-27 | 2025-03-15 | RC03-9500879389-FIXING WBS CODE | RC03-9500879389-FIXING WBS CODE | 3 | 18112 | Reclass | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 900571946775 | AP03 2025 WDAC - | USD | US Dollar | USD | 18112 | 18112 | 18112
9500879389 | 202503 | 2100077618 | Not assigned | IT-FBT0397-OG-US-00 | 2025-02-24 | 2025-03-03 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 3 | -19385.28 | Reversal | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 2100077618174 | AP2-25 2WM | USD | US Dollar | USD | -19385.28 | -19385.28 | -19385.28
9500882917 | 202503 | 2100077618 | Not assigned | IT-FBT0545-OG-US-00 | 2025-02-24 | 2025-03-03 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 3 | -62210 | Reversal | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100077618177 | AP2-25 2WM | USD | US Dollar | USD | -62210 | -62210 | -62210
9500882917 | 202503 | 2100077870 | Not assigned | IT-FBT0545-OG-US-00 | 2025-03-31 | 2025-03-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 3 | 121710 | Accrual | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007787014 | # | USD | US Dollar | USD | 121710 | 121710 | 121710
9500882917 | 202503 | 2100077928 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-01 | 2025-03-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 3 | -16110 | Reversal | 2025 | 2025-03-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 21000779288 | OPEX -T3 ADJ | USD | US Dollar | USD | -16110 | -16110 | -16110
9500879389 | 202505 | 9005790523 | Not assigned | IT-FBT0784-OG-US-00 | 2025-05-22 | 2025-05-15 | RC05-9500879389-FIXING INCORRECT AMOUNT ON RECLASS | RC05-9500879389-FIXING INCORRECT AMOUNT ON RECLASS | 5 | -2286 | Reclass | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010000 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0784-OG-US-00 |  | 9005790523692 | AP05 2025 WDAC - | USD | US Dollar | USD | -2286 | -2286 | -2286
9500882917 | 202505 | 5107435533 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-05-20 | 2025-05-20 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 5 | 20960 | Actual | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51074355332 | C25291704 | USD | US Dollar | USD | 20960 | 20960 | 20960
9500879389 | 202505 | 5107435534 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-05-20 | 2025-05-20 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 5 | 15247.5 | Actual | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51074355342 | C25938904 | USD | US Dollar | USD | 15247.5 | 15247.5 | 15247.5
9500882917 | 202505 | 2100078712 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-28 | 2025-05-05 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 5 | -112062 | Reversal | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007871215 | # | USD | US Dollar | USD | -112062 | -112062 | -112062
9500882917 | 202505 | 2100078772 | Not assigned | IT-FBT0545-OG-US-00 | 2025-04-29 | 2025-05-05 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 5 | 18462 | Accrual | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007877211 | OPEX -T3 ADJ | USD | US Dollar | USD | 18462 | 18462 | 18462
9500882917 | 202505 | 2100078931 | Not assigned | IT-FBT0545-OG-US-00 | 2025-05-27 | 2025-05-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 5 | 140102 | Accrual | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007893113 | # | USD | US Dollar | USD | 140102 | 140102 | 140102
9500882917 | 202505 | 2100079005 | Not assigned | IT-FBT0545-OG-US-00 | 2025-05-28 | 2025-05-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 5 | -18502 | Reversal | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007900510 | OPEX -T3 ADJ | USD | US Dollar | USD | -18502 | -18502 | -18502
9500879389 | 202505 | 2100078708 | Not assigned | IT-FBT0790-OG-US-00 | 2025-04-28 | 2025-05-05 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 5 | -19294.5 | Reversal | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100078708140 | AP4-25 2WM | USD | US Dollar | USD | -19294.5 | -19294.5 | -19294.5
9500879389 | 202505 | 2100078972 | Not assigned | IT-FBT0790-OG-US-00 | 2025-05-27 | 2025-05-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 5 | 20952.78 | Accrual | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100078972119 | AP5-25 2WM | USD | US Dollar | USD | 20952.78 | 20952.78 | 20952.78
9500879389 | 202505 | 9005790523 | Not assigned | IT-FBT0397-OG-US-00 | 2025-05-22 | 2025-05-15 | RC05-9500879389-FIXING INCORRECT AMOUNT ON RECLASS | RC05-9500879389-FIXING INCORRECT AMOUNT ON RECLASS | 5 | 2286 | Reclass | 2025 | 2025-05-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 923 | Managed Services | Managed Services | 41500000 | 2 | 9318 | 10 | ZO | 1400 | United States | AMER | IT-FBT0397-OG-US-00 |  | 9005790523688 | AP05 2025 WDAC - | USD | US Dollar | USD | 2286 | 2286 | 2286
9500882917 | 202506 | 5107443439 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-05-28 | 2025-05-28 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 6 | 27720 | Actual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51074434392 | C25291702 | USD | US Dollar | USD | 27720 | 27720 | 27720
9500882917 | 202506 | 5107470913 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-06-13 | 2025-06-13 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 6 | 27040 | Actual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51074709132 | C258291704 | USD | US Dollar | USD | 27040 | 27040 | 27040
9500882917 | 202506 | 5107471190 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-06-13 | 2025-06-13 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 6 | 48000 | Actual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51074711902 | C25291705 | USD | US Dollar | USD | 48000 | 48000 | 48000
9500879389 | 202506 | 5107471189 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-06-13 | 2025-06-13 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 6 | 11162.5 | Actual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51074711892 | C25938905 | USD | US Dollar | USD | 11162.5 | 11162.5 | 11162.5
9500882917 | 202506 | 2100079100 | Not assigned | IT-FBT0545-OG-US-00 | 2025-05-27 | 2025-06-02 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 6 | -140102 | Reversal | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007910013 | # | USD | US Dollar | USD | -140102 | -140102 | -140102
9500882917 | 202506 | 2100079171 | Not assigned | IT-FBT0545-OG-US-00 | 2025-05-28 | 2025-06-02 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 6 | 18502 | Accrual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210007917110 | OPEX -T3 ADJ | USD | US Dollar | USD | 18502 | 18502 | 18502
9500882917 | 202506 | 2100079327 | Not assigned | IT-FBT0545-OG-US-00 | 2025-06-30 | 2025-06-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 6 | 98592 | Accrual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100079327124 | AP6-25 2WM | USD | US Dollar | USD | 98592 | 98592 | 98592
9500879389 | 202506 | 2100079139 | Not assigned | IT-FBT0790-OG-US-00 | 2025-05-27 | 2025-06-02 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 6 | -20952.78 | Reversal | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100079139119 | AP5-25 2WM | USD | US Dollar | USD | -20952.78 | -20952.78 | -20952.78
9500879389 | 202506 | 2100079327 | Not assigned | IT-FBT0790-OG-US-00 | 2025-06-30 | 2025-06-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 6 | 30922.5 | Accrual | 2025 | 2025-06-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100079327122 | AP6-25 2WM | USD | US Dollar | USD | 30922.5 | 30922.5 | 30922.5
9500882917 | 202509 | 5107592031 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-08-21 | 2025-09-02 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 9 | 2400 | Actual | 2025 | 2025-09-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51075920312 | C25291707 | USD | US Dollar | USD | 2400 | 2400 | 2400
9500882917 | 202509 | 2100080552 | Not assigned | IT-FBT0545-OG-US-00 | 2025-09-29 | 2025-09-15 | PO - 9500882917 - IBM CORP | PO - 9500882917 - IBM CORP | 9 | 57824 | Accrual | 2025 | 2025-09-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 210008055249 | T2 2WM | USD | US Dollar | USD | 57824 | 57824 | 57824
9500879389 | 202509 | 2100080320 | Not assigned | IT-FBT0790-OG-US-00 | 2025-08-25 | 2025-09-01 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 9 | -13632.5 | Reversal | 2025 | 2025-09-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100080320120 | T2 2WM | USD | US Dollar | USD | -13632.5 | -13632.5 | -13632.5
9500879389 | 202509 | 2100080552 | Not assigned | IT-FBT0790-OG-US-00 | 2025-09-29 | 2025-09-15 | PO - 9500879389 - IBM CORP | PO - 9500879389 - IBM CORP | 9 | 13632.5 | Accrual | 2025 | 2025-09-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 210008055250 | T2 2WM | USD | US Dollar | USD | 13632.5 | 13632.5 | 13632.5
9500879389 | 202508 | 5107557829 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-08-12 | 2025-08-12 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 8 | 427.5 | Actual | 2025 | 2025-08-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51075578292 | C25938907 | USD | US Dollar | USD | 427.5 | 427.5 | 427.5
9500882917 | 202508 | 2100080021 | Not assigned | IT-FBT0545-OG-US-00 | 2025-07-28 | 2025-08-04 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 8 | -60224 | Reversal | 2025 | 2025-08-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100080021131 | 2WM OPEX | USD | US Dollar | USD | -60224 | -60224 | -60224
9500879389 | 202508 | 2100080021 | Not assigned | IT-FBT0790-OG-US-00 | 2025-07-28 | 2025-08-04 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 8 | -14060 | Reversal | 2025 | 2025-08-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100080021129 | 2WM OPEX | USD | US Dollar | USD | -14060 | -14060 | -14060
9500879389 | 202508 | 2100080153 | Not assigned | IT-FBT0790-OG-US-00 | 2025-08-25 | 2025-08-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 8 | 13632.5 | Accrual | 2025 | 2025-08-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100080153120 | T2 2WM | USD | US Dollar | USD | 13632.5 | 13632.5 | 13632.5
9500882917 | 202507 | 5107523041 | IBM WW ORDERING AND US INVOICING | IT-FBT0545-OG-US-00 | 2025-07-17 | 2025-07-17 | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | IBM - 2025 S1 COVID APPLICATIONS SUPPORT | 7 | 38368 | Actual | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 51075230412 | C25291706 | USD | US Dollar | USD | 38368 | 38368 | 38368
9500879389 | 202507 | 5107523043 | IBM WW ORDERING AND US INVOICING | IT-FBT0790-OG-US-00 | 2025-07-17 | 2025-07-17 | IBM 2025 S1 - IO SUPPORT | IBM 2025 S1 - IO SUPPORT | 7 | 16862.5 | Actual | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | RE | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 51075230432 | C25938906 | USD | US Dollar | USD | 16862.5 | 16862.5 | 16862.5
9500882917 | 202507 | 2100079612 | Not assigned | IT-FBT0545-OG-US-00 | 2025-06-30 | 2025-07-07 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 7 | -98592 | Reversal | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100079612124 | AP6-25 2WM | USD | US Dollar | USD | -98592 | -98592 | -98592
9500882917 | 202507 | 2100079882 | Not assigned | IT-FBT0545-OG-US-00 | 2025-07-28 | 2025-07-15 | PO- 9500882917 IBM CORP | PO- 9500882917 IBM CORP | 7 | 60224 | Accrual | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0545-OG-US-00 |  | 2100079882131 | 2WM OPEX | USD | US Dollar | USD | 60224 | 60224 | 60224
9500879389 | 202507 | 2100079612 | Not assigned | IT-FBT0790-OG-US-00 | 2025-06-30 | 2025-07-07 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 7 | -30922.5 | Reversal | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100079612122 | AP6-25 2WM | USD | US Dollar | USD | -30922.5 | -30922.5 | -30922.5
9500879389 | 202507 | 2100079882 | Not assigned | IT-FBT0790-OG-US-00 | 2025-07-28 | 2025-07-15 | PO- 9500879389 IBM CORP | PO- 9500879389 IBM CORP | 7 | 14060 | Accrual | 2025 | 2025-07-01 | DIGITAL | IT160 | 2320521 | DeHart, Lynn | Ganesan, Srinivasan | 1400/9318/02/IT160/0002320521 (780) (Net | DIGITAL | CTIES | ERP | DIGITAL SOLUTION DELIVERY | DIGITAL SOLUTION DELIVERY HQ- US | 890 | 915 | Professional Serv-Admin&Commercial | Contractors | 41010100 | 2 | 9318 | 10 | ZY | 1400 | United States | AMER | IT-FBT0790-OG-US-00 |  | 2100079882129 | 2WM OPEX | USD | US Dollar | USD | 14060 | 14060 | 14060